## Tech-Stack
Sno | Technology | Time Taken | Expected Completion
1 | MySQL | 2 Months | March 20th 2026
2 | Spring WebFlux | 2 Months | March 20th 2026
3 | React | 2 Months | March 20th 2026
4 | Spring AI | 1 Month | April 20th 2026
5 | Docker | 1 Month | May 20th 2026
6 | Microservices Kafka | 2 Months | June 20th 2026

## Stages
Sno | Implementation | Description | Completion Date | Status
1 | Spring WebFlux | Industry standard end to end pipeline, one controller, one table CRUD | 2026-02-15
- Controller
- Service
- Controller Advice
- Swagger
- Micrometer
- Prometheus/Grafana
- Logging
- Authentication & Authorization
- Unit Testing
2 | All Database models and queries | All Data points with Swagger | 2026-02-28
3 | Getting Sound and Video Files from browser |  | 2026-03-10
4 | React Component mapping/React Components |  | 2026-03-30
5 | Testing |  |  | Till End of Project
6 | Spring AI | Text/Video/Audio files pipe to AI model | 2026-04-10
7 | Spring AI | Prompting on Text/Video/Audio | 2026-04-20
8 | Docker | Learning Task |  | On Going
9 | Apache Kafka Microsevices | Mid way |  | ??
10 | Payments Module | Along with Docker

## Application Design
Sno | Application | Modules/Workflow | Database | Table | Column | Description
1 | Authentication Server | User management | ems_user_management | Roles |  | User, HR, Applicatoin ADMIN, ADMIN
Users
|  |  |  | Entities/Entity Types/ Entity Properties |  | University, Company, …
|  |  |  | Applications |  | Which applications user has access to
Modules
|  |  |  | Documents |  | Which documents/reports/records user has access to
|  |  |  | Resource Server/Client |  | Resource Server secret
|  |  |  | Key management |  | JWT token generation keys
ems_third_party_authentication
|  |  | ems_activity_logs | Activity Logs
2 | EMOTISense | Video |  |  |  | Needs clarification
|  | AI Interview Feedback | ems_ai_candidate_profile | Technical, Personality/Behavioral, Problem Solving Approaches, Communication, Career path guidence based on market trend, update profile scores based on most recent mock interviews/assessments{figure out formula}, one to one mentoring feedback
|  | AI Resume Evaluator | ems_ai_candidate_profile
|  | AI Resume Builder | ems_ai_candidate_profile
|  | AI Career Counsoler | ems_ai_candidate_profile
|  | AI Audio to Text | ems_ai_candidate_profile
|  | AI Video |  |  |  | Needs clarification
|  | Connects to LinkedIn, Naukri and applies AI | ems_ai_candidate_profile
|  | Candidate Community | ems_candidate_activity
|  | Candidate Blog | ems_candidate_activity
|  | Candidate Management | ems_candidate_activity
|  | Candidate Dashboard | ems_candidate_activity
|  | Candidate Subscription Details | ems_candidate_subscription | gateway, gateway api, api properties, api data, transaction logs, ai summary
|  | Course Integrator |  |  |  | Needs clarification
|  | Candidate manual profile | ems_candidate_profile
|  | User Notification | ems_user_notification
|  | Human generated AI assisted Interview Practice Content | ems_ai_candidate_evaluation_checklist | Tests to evaluate: Technical, Personality/Behavioral, Problem Solving Approaches, Communication, Career path guidence based on market trend, ACCESS TO COMPANIES, AI Powered interviews
|  | Human generated AI assisted Employee expectation/requirements |  |  |  | Disconnenct
|  | AI generate market employement trends |  |  |  | Disconnect: News papers and other employment website APIs/Stock Market trends -> company profile -> company performance -> trend recommendations
|  | AI Powered Resume optimization | ems_resume_optimizer | Original resume, resume modification based on job description, sort resumes based on skills and rating, ai powered employee search tool
|  | AI powered tools for calling third party job portals | ems_thirdparty_job_post | portal lists, api specifications, api properties, data from apis, ai powered data groups{?}
|  | Job posting announcements | ems_jobposting | company, hr user, campus, location, description, skill list, required profile properties
|  | Recuriter Subscription Details |  | gateway, gateway api, api properties, api data, transaction logs, ai summary

## Authentication Server Tasks
Sno | Application | Module/Database | Task | Description | Sequence | Progress | Days Taken | Start Date | Completion Date | Comment
1 | Authentication Server | User management | Create MySQL Docker Image with Volume | Create MySQL database with volumes in docker. Configure PHPMyAdmin in a separate docker instance and connect to this docker image. Create tables and columns. | 1 | Done | 1 | 2026-01-19 | 2026-01-19 | JWT Generation Rotation table pending.
2 | Authentication Server | User management | Database configuration for authentication server | Provide database connection details for Authentication server on first startup. Save details to file. Add unit tests. | 3 |  | 1 | 2026-01-26
3 | Authentication Server | User management | Authentication Management for Authentication Server | Get and add admin user to provided database on first startup. Add unit tests. | 3 |  | 2 | 2026-01-27
4 | Authentication Server | User management | CRUD User/Resource Server/Application/Module/Page/Document | Add CRUD operations for each of the components in User Management. Add unit tests. | 2 | Started | 4 | 2026-01-20 |  | No Security just yet, .permitAll
5 | Authentication Server | User management | Swagger | Add Swagger UI for each of the CRUD operations | 2 | Started | 2 | 2026-01-24
6 | Authentication Server | User management | List API endpoints for Authentication Server | Look into OpenID connect docs | 1 | Done | 1 | 2026-01-18 | 2026-01-18
7 | Authentication Server | User management | User authentication JWT Token Creation | Authenticate a user and create JWT Token for the user based on resources made available to him. | 5 |  | 4 | 2026-01-29
8 | Authentication Server | User management | JWT Token Validation API | Validate JWT token to resource server if requested. | 5 |  | 1 | 2026-02-02
9 | Authentication Server | User management | Third Party Authentication API | Integrate with third party authentication providers | 5 |  | 4 | 2026-02-06
10 | Authentication Server | User management | User Signup | Form based SignUp, Third-party signup | 5 |  | 1 |  |  | Trajectory correction
11 | Authentication Server | User management | User Login | Form based Login, with all tokens sent to UI Client | 5 |  | 1
12 | Authentication Server | User management | Get Public decryption Token | Get JWT public decryption token | 5 |  | 1
13 | Authentication Server | User management | User Token Refresh | Get New Token Using Refresh Token, invalidate old token | 5 |  | 1
14 | Authentication Server | User management | Resource Server Token Refresh | Get New Token Using Refresh Token, invalidate old token, for kafka services | 6 |  | 1
15 | Authentication Server | User management | Swagger integration with Authentication Server | Figure out how to integrate swagger into custom authentication server, and integrate. Think interfaces. | 6 |  | 4
16 | Authentication Server | React User Interface | Write react components | Table, Form, Navigation, Layout, and API calls | 6 |  | 6
17 | Authentication Server | React User Interface
| Authentication Server | User management | Integrate with Kafka |  | 6 |  |  |  |  | ??
| Authentication Server | User management | Actuator |  | 6
| Authentication Server | User management | Micrometer | Add Micrometer for each of the CRUD operations | 6
| Authentication Server | User management | Logger | Add Logger for each of the CRUD operations | 6

## EMOTISense Tasks
Sno | Application | Module/Database | Issue Type | Task | Sequence | Start Date | Completion Date | Comment | Status
| EMOTISense Tasks | Authentication/Authorization |  | Authenticate/Authorize user using JWT and Public key | 1 |  |  |  | Deprecated
| EMOTISense Tasks | CRUD Operations |  | CRUD Operations for each of the records based on authorization, with unit tests | 2 |  |  |  | Deprecated
| EMOTISense Tasks | All AI Modules |  | CRUD Dataset for UI based prompt creation | 3 |  |  |  | Deprecated
| EMOTISense Tasks | CRUD Operations for Audio, Video Files |  | CRUD operations and passing data into AI models | 3 |  |  |  | Deprecated
| EMOTISense Tasks | Create all UI Components |  | Forms, tables, layout, rich text, and API calls | 4 |  |  | Based on feedback | Deprecated
| EMOTISense Tasks | Code the UI |  | Create generic layout fill in details | 4 |  |  | Based on feedback | Deprecated
| EMOTISense Tasks | Prompt engineering Security |  |  | 5 |  |  | On going, never ending | Deprecated
| Templating Engine Tasks | Dummy data generator |  | Talk to Krio generate a dummy data writer application. | 0 | 2026-03-10 | 2026-03-10 | Done, need to do a detailed test | Done
| Templating Engine Tasks | Admin creation |  | Redirect to swagger after admin creation |  | 2026-03-10
| Templating Engine Tasks | Data Validation |  | Use validation error description in Swagger UI, and in general, code missing | 0 | 2026-03-10 | 2026-03-10 | Needs detailed testing | Done
| Templating Engine Tasks | Authorizations Permissions Page |  |  |  | 2026-03-10
| Templating Engine Tasks | Default Data permission groups at table level |  |  |  | 2026-03-10
| Templating Engine Tasks | How to add a record to a group |  | How to grant access to a record in a group, add record to user defined group or one of the public groups. |  | 2026-03-10 | 2026-03-13 |  | Deprecated
| Templating Engine Tasks | Split group table into two |  | Create a new table called group, table, record. At present string concatenation of multiple records, go for one record per record. |  | 2026-03-10 | 2026-03-13 |  | Deprecated
| Templating Engine Tasks | Flag based enable/disable authentication/authorization |  | Enable disable authentaion or authorization in security bean. |  | 2026-03-10
| Templating Engine Tasks | Missing Application Definition JSON |  |  |  | 2026-03-10 | 2026-03-10 | AI is struggling, Application definition split across multiple files | Done
| Templating Engine Tasks | Custom query during application definition stage |  |  |  | 2026-03-10 |  |  | Done
| Templating Engine Tasks | Custom query group during application definition stage |  |  |  | 2026-03-10
| Templating Engine Tasks | Payment gateway integration |  |  |  | 2026-03-10
| Templating Engine Tasks | AI layer integration |  |  |  | 2026-03-10
| Templating Engine Tasks | Change the DB structure, move logging to a different table |  |  |  | 2026-03-10 | 2026-03-10 | Needs detailed testing | Done
| Templating Engine Tasks | Application Definition |  | Functions to perform CRUD on application definitions |  | 2026-03-11 | 2026-03-11 | Needs detailed testing | Done
| Templating Engine Tasks | Query |  | Get the application to implement one to one and one to many relationships reactively. |  | 2026-03-11 |  |  | Duplicate
| Templating Engine Tasks | Application Definition |  | Add dirty and clean tags on application definition objects, so only the onces that were changed are rebuilt. And application definition is written only once. | 5 | 2026-03-11
| Templating Engine Tasks | Application Definition |  | Extend application definition to include custom code. | 6 | 2026-03-11 |  |  | Later, use only sql
| Templating Engine Tasks | Application Definition |  | Move application definition objects to database. | 7 | 2026-03-13 |  | Flop, next version. | Next Version
| Templating Engine Tasks | Authorization |  | No API to create access groups at runtime, groups are prepopulated in database. Admin user or admin group users can grant or revoke access to groups. Create table level access group insert statements when generating code that writes authentication database. | 4 | 2026-03-13 | 2026-03-14 | Needs detailed testing | Done
| Templating Engine Tasks | Authorization |  | Users can grant or revoke access to their individual records only through query in which this record table is the head of the query not individual table records. | 3 | 2026-03-13 | 2026-03-14 | Needs detailed testing | Done
| Templating Engine Tasks | Authorization |  | Make query access a separate grant access, not part of CRUD flow. | 2 | 2026-03-13 | 2026-03-13 | Needs detailed testing | Done
| Templating Engine Tasks | Query Builder |  | App writer needs to build a query from definition given in query layer, have a filters layer as well. Write queries using R2DBC DatabaseClient. | 1 | 2026-03-13 | 2026-03-13 | Needs detailed testing | Done
| Templating Engine Tasks | Database builder |  | Move database definition to JSON, part of application definition, make it more descriptive, then send this definition to database layer to generate actual database file. A little more detail will help React code writer. | 8 | 2026-03-13 |  |  | Next Version
| Templating Engine Tasks | Application Definition |  | Add version on the generated templates within application writer, and add this version to each of the individual components within application definition. | 9 | 2026-03-13 |  |  | Next Version
| Templating Engine Tasks | Query Builder |  | Write a layer for generating default queries. Rules if leaf table, generate query with masters label column inserted. Single master or multiple. If master generate a grouping query with count of child record for each master record. If a master has multiple children use join to combine the counts for each master. Same goes with linked table. | 1 | 2026-03-13 | 2026-03-13 | Needs detailed testing | Done
| Templating Engine Tasks | Application Writer |  | AI is getting stuck on long code and documentation files, need to make it generate smaller chunks. Create a new application from existing. | 10 | 2026-03-13 |  |  | After testing
| Templating Engine Tasks | Authorization |  | Authorization Layer for Community management, is this needed? User groups are already there we need to make creating them automatic for each query. Some way to define a user group. Add friends action, friends table? Community group? Made it part of application definition. | 3 | 2026-03-13 | 2026-03-14 |  | Redundent
| Templating Engine Tasks | Cleanup |  | Cleanup the code remove unnecessary files. |  | 2026-03-14 |  |  | Next Version
| Templating Engine Tasks | Debug |  | Run each and every layer and test, list each layer as a task before starting. |  | 2026-03-14 |  |  | Work in Progress
| Templating Engine Tasks | AI |  | LLM tasks |  | 2026-03-14
| Templating Engine Tasks | UI/UX |  | React |  | 2026-03-14
| Templating Engine Tasks | Mailing |  | Layer to mail and get response |  | 2026-03-14 |  |  | Next Version
| Templating Engine Tasks | Application definition |  | no more deleting existing application definition, database |  | 2026-03-15 |  |  | Next Version
| Templating Engine Tasks | Application Definition |  | Make notes on approach to Spring AI |  | 2026-03-15
| Templating Engine Tasks | Application Definition |  | Make notes on React Redux and application definition |  | 2026-03-15
| Templating Engine Tasks | Application Definition |  | Test Authentication | 3 | 2026-03-16 |  |  | Work in progress
| Templating Engine Tasks | Application Definition |  | Test Create for all components, read code | 4 | 2026-03-16 |  |  | Work in progress
| Templating Engine Tasks | Application Definition |  | Test Read for all components, read code |  | 2026-03-16
| Templating Engine Tasks | Application Definition |  | Test Update for all components, read code |  | 2026-03-16
| Templating Engine Tasks | Application Definition |  | Test Delete for all components, read code |  | 2026-03-16
| Templating Engine Tasks | Application Definition |  | Test Generated reports, read code |  | 2026-03-16
| Templating Engine Tasks | Application Definition |  | Test Authorization, read code |  | 2026-03-16
| Templating Engine Tasks | Bug |  | The application is not sending a proper 401 Unauthorized response when a request has an invalid or missing JWT token. | 2 | 2026-03-16 |  | Add to test cycle | Done
| Templating Engine Tasks | Bug |  | Remove audit fields from DTOs if they're truly in a different database and not needed in responses | 1 | 2026-03-16 |  | Add to test cycle | Done
| Templating Engine Tasks | Bug |  | In short: the authorization-level audit (who tried to access what, and was it granted) is working. But the CRUD activity tracking, login tracking, and the per-record audit columns (createdById, updatedById, createdOn, updatedOn) are all defined but never wired in. | 0 | 2026-03-16 |  | Add to test cycle | Done
| Templating Engine Tasks | Application Code |  | Read code before starting full testing | 3 | 2026-03-16 |  |  | Work in progress
| Templating Engine Tasks | Layer |  | Have a layer that allows creation of only one record(or n configurable) per user in a table, given the table. |  | 2026-03-17 |  |  | Next Version
| Templating Engine Tasks | Authentication |  | Authorization is missing | 0 | 2026-03-17 |  | Flag was disabled by default | Done
| Templating Engine Tasks | Validation |  | Validation messages missing | 0 | 2026-03-17 |  | Messages present, too short | Done
| Templating Engine Tasks | Naming conventions |  | Make all files belonging to configuration and security layer start with AppSys<<ClassName>>. |  | 2026-03-18 |  |  | Next Version
| Templating Engine Tasks | Authentication |  | Group Level access is restricted to service, we need a layer for controller level access. Otherwise unnecessary DB queries. Need a simplified implementation that works with exisiting groups. JWT is getting involved, do we go JWT route? Or just DB replication? We are not behind VPN. Or should we have a session store? Or just leave it as is? |  | 2026-03-19 |  |  | Next Version
| Templating Engine Tasks | DDoS |  | Preventing DDoS attacks. |  | 2026-03-19 |  |  | Next Version
| Templating Engine Tasks | Pending |  | There are some todos in the code, fix them. |  | 2026-03-19 |  |  | Work in progress
| Templating Engine Tasks | Authorization |  | Check if JWT is being cleared after logout. |  | 2026-03-20
| Templating Engine Tasks | Logging |  | Check if logging has any CUD API calls, they should not. |  | 2026-03-20
| Templating Engine Tasks | React |  | Write react components definition prompts. |  | 2026-03-21 | 2026-03-28 |  | Done
| Templating Engine Tasks | React |  | Write wiring between redux and ui componets. |  | 2026-03-21 | 2026-03-28 |  | Done
| Templating Engine Tasks | React |  | Write compositions between components. |  | 2026-03-21 |  |  | Test
| Templating Engine Tasks | React |  | Map API calls to redux to components. |  | 2026-03-21 | 2026-03-28 |  | Done
| Templating Engine Tasks | WebFlux |  | Permissions are shared with UI as allowed API calls in JSON, I think we have to make this change in backend, add an endpoint that lists out API endpoints user can access. |  | 2026-03-21
| Templating Engine Tasks | Testing tool |  | Extend the testing tool by giving it access to backend. |  | 2026-03-21
| Templating Engine Tasks | Authorization |  | Simplify authorization layer, have sub groups of two layers. One access control to controller call, second access control to record level. |  | 2026-03-21 |  |  | Work in Progress
| Templating Engine Tasks | Automated Testing |  | Extend it to take screenshots and add button clicks |  | 2026-03-21 | 2026-03-28 | Even better it can record videos of testing. | Done
| Templating Engine Tasks | Theming Emulator |  | Make Kiro write a webscrapper with the aim of copying styles from other websites. |  | 2026-03-21 |  |  | Test
| Templating Engine Tasks | React Writer |  | Update the application to generate one application per layout style/theming style. Or have a button on the application to switch between themes. |  | 2026-03-21 | 2026-03-28 |  | Redundent
| Templating Engine Tasks | WebFlux |  | Make Create, Update, and Delete operations pipelined and transactional, for more expansive queries. |  | 2026-03-23
| Templating Engine Tasks | WebFlux |  | Dynamic Form generator component, webflux and React |  | 2026-03-23
|  | WebFlux |  | Backend has not implemented Referesh token in JWT |  | 2026-03-23 |  |  | Check
| Templating Engine Tasks | React | Bug | Routes not working |  | 2026-03-23 | 2026-03-28 |  | Done